## Sheet1
Timeline Chart Part-1
Activity Key-
Weeks |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Task: Person | [29 empty] | Pre-Game
A : | Rubab
B: | Eshmom | [28 empty] | A : | Overall Planning
C : | Shohid | [28 empty] | B : | High-level architecture design
D : | Shohid | [28 empty] | C : | Update Product Backlog
E : | Rubab
F : | Eshmom | [28 empty] | Development Phase (In-Game)
G : | Shohid
H : | Rubab | [28 empty] | D : | Sprint Backlog List
I : | Rubab
J : | Eshmom | [29 empty] | Module-1
K : | Shohid | [28 empty] | E : | Analysis
L : | Rubab | [28 empty] | F : | Design
M : | Rubab | [28 empty] | G : | Development
N : | Eshmom | [28 empty] | H : | Testing
O : | Shohid
P : | Rubab | [29 empty] | Module-2
Q : | Shohid | [28 empty] | I : | Analysis
R : | Rubab | [28 empty] | J : | Design
S : | Eshmom | [28 empty] | K : | Development
T : | Rubab | [28 empty] | L : | Testing
|  | 26: Development Team- |  | Module-3
[30 empty] | M : | Analysis
|  | 26: Rubab | N : | Design
|  | 26: Eshmom | O : | Development
|  | 26: Shohid | P : | Testing
Post-Game
[30 empty] | Q : | System Intregation
[30 empty] | R : | System Testing
[30 empty] | S : | Documentation
[30 empty] | T : | Final Release

## Sheet2
Timeline Chart Part-2
Weeks | Week-1 |  |  |  |  | Week-2 |  |  |  |  | Week-3 |  |  |  |  | Week-4 |  |  |  |  | Week-5 |  |  |  |  | Week-6 |  |  |  |  | Week-7 |  |  |  |  | Week-8 |  |  |  |  | Week-9 |  |  |  |  | Week-10 |  |  |  |  | Week-11 |  |  |  |  | Week-12 |  |  |  |  | Week-13 |  |  |  |  | Week-14 |  |  |  |  | Week-15 |  |  |  |  | Week-16 |  |  |  |  | Week-17 |  |  |  |  | Week-18 |  |  |  |  | Week-19 |  |  |  |  | Week-20 |  |  |  |  | Week-21 |  |  |  |  | Week-22 |  |  |  |  | Week-23 |  |  |  |  | Week-24 |  |  |  |  | Week-25 |  |  |  |  | Week-26 |  |  |  |  | Week-27 |  |  |  |  | Week-28
Work Tasks | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
1.1.1 Planning | bar: Week-1 1 to Week-1 3
1.1.2 Cost & Schedule Management | bar: Week-1 2 to Week-2 1
1.1.3 Scope Management | bar: Week-1 5 to Week-2 3
1.1.4 Task Management | bar: Week-2 3 to Week-2 5
1.1.5 Project Communication | bar: Week-2 5 to Week-3 2
1.1.6 Risk Management | bar: Week-2 5 to Week-3 4
1.1.7 Quality Management | bar: Week-3 1 to Week-3 3
Milestone : Project Management Defined
1.2.1 Technical plannning | bar: Week-3 4 to Week-4 3
1.2.2 Technical supervision | bar: Week-3 5 to Week-4 4
1.2.3 Business requirement definition | bar: Week-4 4 to Week-5 1
1.2.4 System Architecture & Top-level design | bar: Week-5 1 to Week-6 1
Milestone : System Engineering Complete
1.3.1.1 Software Requirement Specification | bar: Week-6 2 to Week-9 1
1.3.1.2 Software Prototyping | bar: Week-8 2 to Week-10 1
1.3.1.3 Software unit detailed design | bar: Week-9 5 to Week-11 5
Milestone : Software Design Complete
1.3.2.1 Software unit coding | bar: Week-12 1 to Week-14 1
1.3.2.2 Software unit debugging | bar: Week-13 2 to Week-15 1
Milestone : Software Build Complete
1.3.3.1 Unit testing planning | bar: Week-15 2 to Week-16 4
1.3.3.2 Unit test case preparation | bar: Week-15 5 to Week-16 5
1.3.3.3 Unit testing conduct | bar: Week-16 4 to Week-18 2
1.3.3.4 Unit test records | bar: Week-18 1 to Week-18 5
Milestone : Unit Testing Complete
1.4.1 Deliverables tracking | bar: Week-19 1 to Week-20 2
Milestone : Deliverables Management Defined
1.5.1 User feedback | bar: Week-20 3 to Week-21 2
1.5.2 Development tools and utilities | bar: Week-21 1 to Week-21 5
1.5.3 Team technical training | bar: Week-21 3 to Week-22 2
1.5.4 User training session | bar: Week-21 5 to Week-22 4
1.5.5 Configuration management | bar: Week-22 1 to Week-23 1
Milestone : Support services Defined
1.6.1 Module & Subsystem Testing | bar: Week-23 2 to Week-23 5
1.6.2 System integration Testing | bar: Week-24 1 to Week-24 4
1.6.3 Acceptance Testing | bar: Week-24 5 to Week-25 3
1.6.4 Defect Tracking | bar: Week-25 4 to Week-26 1
Milestone : System Testing Complete
1.7.1 Installation Planning | bar: Week-25 5 to Week-27 1
1.7.2 User Support documentation | bar: Week-26 3 to Week-27 3
1.7.3 User communication & traning | bar: Week-26 5 to Week-27 3
1.7.4 Installation management | bar: Week-27 2 to Week-27 5
1.7.5 Installation testing and verification | bar: Week-27 4 to Week-28 1
1.7.6 Installation performance monitoring | bar: Week-28 2 to Week-28 5
Milestone : Installation Complete